## Gantt Chart
# | Epics and Sub Tasks | Start Date | End Date | April | [8 empty] | May | [30 empty] | June | [29 empty] | July
|  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 14
|  |  |  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 2
1 | Onboarding
1.1 | Onboarding, Office And Laptop Access | 2024-04-22 | 2024-04-23 | bar: Week 1 22 to Week 1 23
1.2 | Password And Authentication Set Up | 2024-04-23 | 2024-04-24 | bar: Week 1 23 to Week 1 24
1.3 | Connect To Confluence And Jira Set Up | 2024-04-24 | 2024-04-24 | bar: Week 1 24
2 | Business Understanding
2.1 | Access To Bureau Data And Team Data Information | 2024-04-24 | 2024-04-25 | bar: Week 1 24 to Week 1 25
2.2 | Problem Statement And Assess Current Situation | 2024-04-25 | 2024-04-29 | bar: Week 1 25 to Week 2 29
2.2 | Produce Project Plan | 2024-04-29 | 2024-05-05 | bar: Week 2 29 to Week 2 5
2.3 | Literature Review | 2024-04-29 | 2024-07-13
3 | Data Acquisition and Understanding
3.1 | Connection To AWS Sage Maker, And Creation Of Persistant Kernal | 2024-05-05 | 2024-05-06 | bar: Week 2 5 to Week 3 6
3.2 | Install Necessary Configurations And Data Acquistion | 2024-05-06 | 1900-01-02 | bar: Week 3 6 to Week 3 9
3.3 | Initial Data Overview And Terminology Understanding | 2024-05-09 | 2024-05-13 | bar: Week 3 9 to Week 4 13
3.4 | Explore And Verify Data Quality | 2024-05-09 | 2024-05-13 | bar: Week 3 9 to Week 4 13
4 | Experiment 1 - Data Formatting and Creation of Monthly Aggregated Attributes
4.1 | Assess Data Structure And Complete Data Formatting | 2024-05-14 | 2024-05-21 | bar: Week 4 14 to Week 5 21
4.2 | Implementation Of The Ageing Pipeline | 2024-05-21 | 2024-05-30 | bar: Week 5 21 to Week 6 30
4.3 | Create Monthly Aggregated Attributes using nb_Acc, WSRatio, CBal, BBal, DBal and CLmt | 2024-05-30 | 2024-06-06 | bar: Week 6 30 to Week 7 6
5 | Experiment 1 - Create Time-Series From Monthly Aggregated Attributes
5.1 | Creation Of Single Time-Series Per Consumer (24 months) | 2024-06-06 | 2024-06-08 | bar: Week 7 6 to Week 7 8
6 | Experiment 1 - Implement Time-Series Clustering and Analysis (Modelling)
6.1 | Implement K-Means Algorithm With Euclidean Similarity Measure | 2024-06-08 | 2024-06-11 | bar: Week 7 8 to Week 8 11
6.2 | Cluster Output Plots And Analysis | 2024-06-11 | 2024-06-13 | bar: Week 8 11 to Week 8 13
7 | Experiment 1 - Derive Cluster-Based Attributes
7.1 | Compute The Distance Of Each Time-Series From Each Centroid - Single Time Series | 2024-06-13 | 2024-06-14 | bar: Week 8 13 to Week 8 14
8 | Experiment 1 - Implement Random Forest to Predict Default Probability
8.1 | Implement Random Forest To Predict Default Using Cluster-Based Attributes | 2024-06-15 | 2024-06-17 | bar: Week 8 15 to Week 9 17
8.2 | Random Forest Output Plots And Analysis | 2024-06-17 | 2024-06-19 | bar: Week 9 17 to Week 9 19
10 | Delphi Model - Implement Logistic Regression to Predict Default Probability
9.1 | Implement Logistic Regression To Predict Default Using Delphi Attributes and Provided Pre-Processing | 2024-06-20 | 2024-06-25 | bar: Week 9 20 to Week 10 25
9.2 | Random Forest Output Plots And Analysis | 2024-06-25 | 2024-06-27 | bar: Week 10 25 to Week 10 27
10 | Experiment 1 and Delphi Model - Run Notebooks as a Job
10.1 | Run Experiment 1 And Delphi Notebook On The Entire Row Using SageMaker Notebook Jobs | 2024-06-27 | 2024-06-28 | bar: Week 10 27 to Week 10 28
10.2 | Review Results For Experiment 1 And Comparison With Delphi Model | 2024-06-28 | 2024-06-30 | bar: Week 10 28 to Week 10 30
11 | Experiment 2 - Data Formatting and Creation of Monthly Aggregated Attributes
11.1 | Assess Data Structure And Complete Data Formatting | 2024-07-01 | 2024-07-01 | bar: Week 11 1
11.2 | Implementation Of The Ageing Pipeline | 2024-07-01 | 2024-07-01 | bar: Week 11 1
11.3 | Add Additional Monhtly Aggregated Attributes (ArrBal, DefBal, TtlBal and CLU) | 2024-07-01 | 2024-07-02 | bar: Week 11 1 to Week 11 2
11 | Experiment 2 - Create Time-Series From Monthly Aggregated Attributes
11.1 | Creation Of Single Time-Series Per Consumer (24 Months) | 2024-07-03 | 2024-07-03 | bar: Week 11 3
11.2 | Creation Of Sub-Sequences Of Segment Length 6 Months And Overlap Of 3 Months | 2024-07-03 | 2024-07-04 | bar: Week 11 3 to Week 11 4
12 | Experiment 2 - Implement Time-Series Clustering and Analysis (Modelling)
12.1 | Implement K-Means Algorithm With Euclidean Similarity Measure | 2024-07-05 | 2024-07-05 | bar: Week 11 5
12.2 | Cluster Output Plots And Analysis | 2024-07-05 | 2024-07-06 | bar: Week 11 5 to Week 11 6
13 | Experiment 2 - Derive Cluster-Based Attributes
13.1 | Compute the Distance of Each Subsequence from Each Centroid - Multiple Time Series | 2024-07-06 | 2024-07-09 | bar: Week 11 7 to Week 12 9
14 | Experiment 2 - Implement Logistic Regression to Predict Default Probability
14.1 | Implement Logistic Regression To Predict Default Using Cluster-Based Attributes | 2024-07-10 | 2024-07-11 | bar: Week 12 10 to Week 12 11
14.2 | Logistic Regression Output Plots And Analysis | 2024-07-12 | 2024-07-13 | bar: Week 12 12 to Week 12 13
14.3 | Consumer Transition And Journey Analysis | 2024-07-14 | 2024-07-16 | bar: Week 12 14 to Week 13 16
14 | Experiment 2 - Run Notebooks as a Job
14.1 | Run Experiment 2 On The Entire Row Using SageMaker Notebook Jobs | 2024-07-17 | 2024-07-19 | bar: Week 13 17 to Week 13 19
14.2 | Review Results For Experiment 2, Experiment 1 And Comparison With Delphi Model | 2024-07-19 | 2024-07-23 | bar: Week 13 19 to Week 14 2
15 | Documentation and Customer Acceptance
15.1 | Report And Presentation Structure | 2024-06-10 | 2024-08-01 | bar: Week 8 10 to Week 14 2
15.2 | Presentation to Stakeholders and Delphi Team | 2024-07-23 | 2024-07-25 | bar: Week 14 23 to Week 14 25